## Slide 1: Houston GPS Timeline: Getting Started
Spring/Summer 2014
June 2014: Houston GPS representatives attended a Complete College America GPS Institute
Fall 2014
March 2015: grant received from Houston Endowment to develop proactive solutions for improving student success among Houston area students
March 2014: Inaugural meeting held at the University of Houston to examine Guided Pathways to Success Strategies
July 2014: Memorandum of Understanding was signed by Houston GPS institution Chancellors and Presidents
Spring 2015
September 2014: Houston GPS representatives attended Complete College America Math Pathways Institute

## Slide 2: Houston GPS Timeline: Establishing an Evidence-Based Plan
Spring/Summer 2015
June 2015: Meeting with institutional leaders to discuss progress and next steps
Summer 2015: Campus Coordinators appointed, Institutional Teams and Task Force Groups formed
August 2015: Houston GPS representatives attended CCA GPS Leader meeting
September 2015: Houston GPS Fall Planning Academy
Fall 2015: Monthly Institutional Team and Task Force Group meetings
Spring 2016
February 2016: Houston GPS Spring Academy
February 2016: Task Force Plans completed
March 2016: Institutional Plans completed
Spring 2015: Review of persistence/graduation studies focused on the Houston area
Fall 2015
January 2016: Cross-institutional technology vendor demonstration meeting

## Slide 3: Houston GPS Timeline: Implementation Progress and Milestones
April 2016: Proactive Advising Symposium, Corequisite Remediation Policy Institute
May 2016: Math Pathways Report released
May 2016: Houston GPS became the 40th member of CCA’s Alliance of States
June 2016: Houston GPS representatives attended CCA 15 to Finish Policy Institute
June 2016: Houston GPS Technology Request for Information released
Fall/Winter 2016
September 2016: Houston GPS became a participant in CCA’s Purpose First network
September 2016: Institutional 5-year targets set for Houston GPS outcome measures
July 2016: Implementation progress monitoring plan established
October 2016: Degree Maps Coordinating Committee met to assess Business maps
November 2016: Houston GPS Alliance Team atte0nded CCA’s Annual Convening
Spring 2017
February 2017: Houston GPS CAO’s met to discuss technology strategies
February 2017: Alliance Liaison and UH Senior Vice President for Academic Affairs and Provost Dr. Paula Myrick Short presented a session at the quarterly University of Houston System Board of Regents meeting on Houston GPS
March 2017: Houston GPS Momentum Year Symposium
Summer 2016
June 2016: Meeting with Houston GPS leaders to discuss next steps